## PROJECT 1
[9 empty] | BILLING STAGE | 100% | 50% | 100% | 50% | 100% | 100%
[9 empty] | TOTAL DELIVERABLES | 6 | 3 | 6 | 3 | 6 | 6
PROJECT NAME | DESCRIPTION | PROJECT MANAGER NAME | BUILDING | FORMAT | REVISION IN PRIMARY SUBMISSION | REVISION IN GFC SUBMISSION | PRIMARY SUBMISSION STATUS | GFC SUBMISSION STATUS | SITE EXICUTION STATUS | PRIMARY COMPLETION AT THIS STAGE | PRIMARY % COMPLETION AT THIS STAGE | GFC COMPLETION AT THIS STAGE | GFC % COMPLETION AT THIS STAGE | SITE EXICUTION COMPLETION AT THIS STAGE | SITE EXICUTION % COMPLETION AT THIS STAGE
A | LOAD CAL SHEET | ABCD | PROJECT | EXCEL | R0 | R1 | DONE | PENDING | DONE | 1 | 16.67% | 0 | 0% | 1 | 16.67%
A | EC CALCULATIONS SHEET | ABCD | PROJECT | EXCEL |  |  | DONE | DONE | DONE | 1 | 16.67% | 1 | 16.67% | 1 | 16.67%
A | EXTERNAL AREA ELECTRICAL BOQ & ESTIMATE | ABCD | PROJECT | EXCEL |  |  | DONE | PENDING | DONE | 1 | 16.67% | 0 | 0% | 1 | 16.67%
A | PHASE WISE - ELECTRICAL BOQ & ESTIMATE | ABCD | PROJECT | DOCUMENT |  |  | PENDING | DONE | DONE | 0 | 0% | 1 | 16.67% | 1 | 16.67%
A | TENDER DOCUMENT | ABCD | PROJECT | DOCUMENT |  |  | PENDING | DONE | DONE | 0 | 0% | 1 | 16.67% | 1 | 16.67%
A | TECHNICAL SEPCIFICATIONS | ABCD | PROJECT | EXCEL |  |  | PENDING | PENDING | DONE | 0 | 0% | 0 | 0% | 1 | 16.67%
A | CABLE SCHEDULE | ABCD | PROJECT | EXCEL | [5 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | MAIN SINGLE LINE DIAGRAM | ABCD | PROJECT | DWG | [5 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | HIGH RISE SINGLE LINE DIAGRAM | ABCD | PROJECT | DWG | [5 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | FIRE ALARM SYSTEM- SLD | ABCD | PROJECT | DWG | [5 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | EARTHING SYSTEM SLD | ABCD | PROJECT | DWG | [5 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | EXTERNAL AREA LIGHTING DB SLD | ABCD | PROJECT | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | LANDSCAPE AREA LIGHTING SLD | ABCD | PROJECT | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | CLUB HOUSE DB SLD | ABCD | PROJECT | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | SUBSTATION LAYOUT | ABCD | PROJECT | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | SUBSTATION LAYOUT WITH ELEVATIONS & SECTION | ABCD | PROJECT | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | CLUB HOUSE CONTROL LAYOUT | ABCD | PROJECT | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | CLUB HOUSE CONDUIT LAYOUT | ABCD | PROJECT | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | RCC HUME PIPE LAYOUT FOR ELECT & LV | ABCD | PROJECT | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | EXTERNAL AREA LIGHTNG LAYOUT | ABCD | PROJECT | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | BUILDING WISE FIRE ALARM SYSTEM LAYOUT | ABCD | PROJECT | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | ELECTRICAL LAYOUT FOR LIFT ROOM | ABCD | PROJECT | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | ELECTRICAL LAYOUTS FOR PUMP ROOMS | ABCD | PROJECT | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | LIGHTNING ARRESTOR LAYOUT | ABCD | PROJECT | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | EARTHING SYSTEM LAYOUT | ABCD | PROJECT | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | LANDSCAPE AREA LIGHTING LAYOUT | ABCD | PROJECT | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | ENTRANCE GATE LIGTHING LAYOUT | ABCD | PROJECT | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | SAMPLE FLAT DB SLD | ABCD | A | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | BUILDING WISE- FLAT INTERNAL DB SLD | ABCD | A | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | BUILDINGWISE - COMMON METER DB SLD | ABCD | A | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | METER PANEL WISE SINGLE LINE DIAGRAM | ABCD | A | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | BUILDING WISE -FIRE ALRM SYSTEM BOQ & ESTIMATE | ABCD | A | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | BUILDING WISE - ODD FLOOR SWITCH BOARD DETAILS | ABCD | A | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | BUILDING WISE -EVEN FLOOR SWITCH BOARD DETAILS | ABCD | A | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | SAMPLE FLAT SWITCH BOARD DETAILS | ABCD | A | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | SAMPLE FLAT ELECTRICAL BOQ | ABCD | A | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | BUILDING WISE - ELECTRICAL BOQ & ESTIMATE | ABCD | A | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | PARKING FLOOR CONTROL LAYOUTS - BASEMENT-2 | ABCD | A | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | PARKING FLOOR CONTROL LAYOUTS - BASEMENT-1 | ABCD | A | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | PARKING FLOOR CONTROL LAYOUTS - LOWER GROUND FLOOR | ABCD | A | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | PARKING FLOOR CONTROL LAYOUTS - UPPER GROUND FLOOR | ABCD | A | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | BUILDING WISE ODD FLOOR CONTROL LAYOUT | ABCD | A | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | BUILDING WISE EVEN FLOOR CONTROL LAYOUT | ABCD | A | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | REFUSE FLOOR CONTROL LAYOUT | ABCD | A | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | TERRACE FLOOR CONTROL LAYOUT | ABCD | A | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | PARKING FLOOR CONDUIT LAYOUTS - BASEMENT-2 | ABCD | A | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | PARKING FLOOR CONDUIT LAYOUTS - BASEMENT-1 | ABCD | A | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | PARKING FLOOR CONDUIT LAYOUTS - LOWER GROUND FLOOR | ABCD | A | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | PARKING FLOOR CONDUIT LAYOUTS - UPPER GROUND FLOOR | ABCD | A | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | BUILDING WISE ODD FLOOR CONDUIT LAYOUT | ABCD | A | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | BUILDING WISE EVEN FLOOR CONDUIT LAYOUT | ABCD | A | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | REFUSE FLOOR CONDUIT LAYOUT | ABCD | A | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | METER ROOM LAYOUT | ABCD | A | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | METER ROOM ELEVATION LAYOUT | ABCD | A | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | ELECTRICAL DUCT LOCATION LAYOUT | ABCD | A | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | CABLE TRAY LAYOUT IN METER PANEL ROOM | ABCD | A | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | CABLE TRAY LAYOUT FROM METER PANEL TO ELECTRICAL DUCT | ABCD | A | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | CABLE TRAY LAYOUT FOR PARKING FLOOR | ABCD | A | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | CABLE TRAY LAYOUT FOR ODD FLOOR | ABCD | A | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | CABLE TRAY LAYOUT FOR EVEN FLOOR | ABCD | A | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | SAMPLE FLAT CONTROL LAYOUT | ABCD | A | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | SAMPLE FLAT CONDUIT LAYOUT | ABCD | A | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | WALL ELEVATIONS DRAWING FOR SAMPLE FLAT | ABCD | A | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | SLEEVES LAYOUT | ABCD | A | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | RACEWAY LAYOUT | ABCD | A | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | BUS BAR TRUNCKING LAYOUT | ABCD | A | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | BUILDING WISE- PARKING FLOOR SLAB CHECK | ABCD | A | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | BUILDING WISE ODD FLOOR SLAB CHECK | ABCD | A | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | BUILDING WISE EVEN FLOOR SLAB CHECK | ABCD | A | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | SAMPLE FLAT CHECKING | ABCD | A | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | BUILDING WISE ODD FLOOR WALL PIPING CHECKING | ABCD | A | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | BUILDING WISE EVEN FLOOR WALL PIPING CHECK | ABCD | A | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%
A | METER PANEL GA DRAWING | ABCD | A | [6 empty] | 0 | 0% | 0 | 0% | 0 | 0%

## Sheet2
COMMON | BUILDING WISE | DRAWING | DOCUMENT
|  | 0100- 002-01- MAIN SINGLE LINE DIAGRAM | 0100- 001-01- LOAD CALCULATION
|  | 0100- 002-02- SINGLE LINE DIAGRAM FOR FIRE ALARM SYSTEM | 0100- 001-02- EC CALCULATION
|  | 0100- 002-03- TRANSFORMER SUBSTAION LAYOUT | 0100- 001-03- TENDER DOCUMENT
|  | 0100- 002-04-DG SET LOACTION LAYOUT | 0100- 001-04- TECHNICAL SPECIFICATIONS
0100- 001-05- ELECTRICAL BLOCK ESTIMATE
0100- 001-06- CABLE SCHEDULE
| E - BUILDING | 0100- 205-01-E BUILDING- LOWER GROUND FLOOR CONTROL & CONDUIT LAYOUT | 0100- 105-01- E BUILDING- ELECTRICAL BOQ & ESTIMATE
|  | 0100- 205-02-E BUILDING- UPPER GROUND CONTROL & CONDUIT LAYOUT | 0100- 105-02- E BUILDING- FIRE ALARM SYSTEM BOQ & ESTIMATE | Active
|  | 0100- 205-03-E BUILDING- GROUND FLOOR CONTROL & CONDUIT LAYOUT | 0100- 105-03- E BUILDING- CCTV SYSTEM BOQ & ESTIMATE | Active
|  | 0100- 205-04-E BUILDING- FIRST FLOOR CONTROL & CONDUIT LAYOUT | 0100- 105-04- E BUILDING- TYPICAL 1RK FLATS SWITCH BOARD DETAILS | Active
|  | 0100- 205-05- E BUILDING- TYPICAL EVEN FLOOR CONTROL & CONDUIT LAYOUT | 0100- 105-05- E BUILDING- TYPICAL 1 BHK FLATS SWITCH BOARD DETAILS | Active
|  | 0100- 205-06- E BUILDING- TYPICAL ODD FLOOR CONTROL LAYOUT | 0100- 105-06- E BUILDING- TYPICAL 2 BHK FLATS SWITCH BOARD DETAILS
|  | 0100- 205-07- E BUILDING- SAMPLE FLAT CONTROL & CONDUIT LAYOUT | 0100- 105-07- E BUILDING- TYPICAL 3 BHK FLATS SWITCH BOARD DETAILS
0100- 205-08- E BUILDING- REFUSE FLOOR-1 CONTROL & CONDUIT LAYOUT
0100- 205-09- E BUILDING- REFUSE FLOOR-2 CONTROL & CONDUIT LAYOUT
0100- 205-10- E BUILDING- METER PANEL ROOM LAYOUT
0100- 205-11- E BUILDING- ELECTRICAL & LV DUCT LOCATION LAYOUT
0100- 205-12- E BUILDING- FIRE ALARM SYSTEM LAYOUT
0100- 205-13- E BUILDING- CCTV SYSTEM LAYOUT
0100- 205-14- E BUILDING- FLAT INTERNAL SLD FOR 1RK FLATS
0100- 205-15- E BUILDING- FLAT INTERNAL SLD FOR 1 BHK FLATS
0100- 205-16- E BUILDING- FLAT INTERNAL SLD FOR 2 BHK FLATS
0100- 205-17- E BUILDING- FLAT INTERNAL SLD FOR 3 BHK FLATS
0100- 205-18- E BUILDING- METER PANEL SLD
0100- 205-19- E BUILDING-CABLE TRAY LAYOUT FROM METER PANEL TO DUCT
0100- 205-20- E BUILDING-COMMON METER DB SLD
0100- 205-21- E BUILDING-TERRACE FLOOR LIGHTING & POWER LAYOUT
| F - BUILDING | 0100- 206-01-F BUILDING- LOWER GROUND FLOOR CONTROL & CONDUIT LAYOUT | 0100- 106-01- F BUILDING- ELECTRICAL BOQ & ESTIMATE
|  | 0100- 206-02-F BUILDING- UPPER GROUND CONTROL & CONDUIT LAYOUT | 0100- 106-02- F BUILDING- FIRE ALARM SYSTEM BOQ & ESTIMATE
|  | 0100- 206-03-F BUILDING- GROUND FLOOR CONTROL & CONDUIT LAYOUT | 0100- 106-03- F BUILDING- CCTV SYSTEM BOQ & ESTIMATE
|  | 0100- 206-04-F BUILDING- FIRST FLOOR CONTROL & CONDUIT LAYOUT | 0100- 106-04- F BUILDING- TYPICAL 1RK FLATS SWITCH BOARD DETAILS
|  | 0100- 206-05- F BUILDING- TYPICAL EVEN FLOOR CONTROL & CONDUIT LAYOUT | 0100- 106-05- F BUILDING- TYPICAL 1 BHK FLATS SWITCH BOARD DETAILS
|  | 0100- 206-06- F BUILDING- TYPICAL ODD FLOOR CONTROL LAYOUT | 0100- 106-06- F BUILDING- TYPICAL 2 BHK FLATS SWITCH BOARD DETAILS
|  | 0100- 206-07- F BUILDING- SAMPLE FLAT CONTROL & CONDUIT LAYOUT | 0100- 106-07- F BUILDING- TYPICAL 3 BHK FLATS SWITCH BOARD DETAILS
0100- 206-08- F BUILDING- REFUSE FLOOR-1 CONTROL & CONDUIT LAYOUT
0100- 206-09- F BUILDING- REFUSE FLOOR-2 CONTROL & CONDUIT LAYOUT
0100- 206-10- F BUILDING- METER PANEL ROOM LAYOUT
0100- 206-11- F BUILDING- ELECTRICAL & LV DUCT LOCATION LAYOUT
0100- 206-12- F BUILDING- FIRE ALARM SYSTEM LAYOUT
0100- 206-13- F BUILDING- CCTV SYSTEM LAYOUT
0100- 206-14- F BUILDING- FLAT INTERNAL SLD FOR 1RK FLATS
0100- 206-15- F BUILDING- FLAT INTERNAL SLD FOR 1 BHK FLATS
0100- 206-16- F BUILDING- FLAT INTERNAL SLD FOR 2 BHK FLATS
0100- 206-17- F BUILDING- FLAT INTERNAL SLD FOR 3 BHK FLATS
0100- 206-18- F BUILDING- METER PANEL SLD
0100- 206-19- F BUILDING-CABLE TRAY LAYOUT FROM METER PANEL TO DUCT
0100- 206-20- F BUILDING-COMMON METER DB SLD
0100- 206-21- F BUILDING-TERRACE FLOOR LIGHTING & POWER LAYOUT
| G - BUILDING | 0100- 207-01-G BUILDING- LOWER GROUND FLOOR CONTROL & CONDUIT LAYOUT | 0100- 107-01- G BUILDING - ELECTRICAL BOQ & ESTIMATE
|  | 0100- 207-02-G BUILDING- UPPER GROUND CONTROL & CONDUIT LAYOUT | 0100- 107-02- G BUILDING - FIRE ALARM SYSTEM BOQ & ESTIMATE
|  | 0100- 207-03-G BUILDING- GROUND FLOOR CONTROL & CONDUIT LAYOUT | 0100- 107-03- G BUILDING - CCTV SYSTEM BOQ & ESTIMATE
|  | 0100- 207-04-G BUILDING- FIRST FLOOR CONTROL & CONDUIT LAYOUT | 0100- 107-04- G BUILDING - TYPICAL 1RK FLATS SWITCH BOARD DETAILS
|  | 0100- 207-05- G BUILDING- TYPICAL EVEN FLOOR CONTROL & CONDUIT LAYOUT | 0100- 107-05- G BUILDING - TYPICAL 1 BHK FLATS SWITCH BOARD DETAILS
|  | 0100- 207-06- G BUILDING- TYPICAL ODD FLOOR CONTROL LAYOUT | 0100- 107-06- G BUILDING - TYPICAL 2 BHK FLATS SWITCH BOARD DETAILS
|  | 0100- 207-07- G BUILDING- SAMPLE FLAT CONTROL & CONDUIT LAYOUT | 0100- 107-07- G BUILDING - TYPICAL 3 BHK FLATS SWITCH BOARD DETAILS
0100- 207-08- G BUILDING- REFUSE FLOOR-1 CONTROL & CONDUIT LAYOUT
0100- 207-09- G BUILDING- REFUSE FLOOR-2 CONTROL & CONDUIT LAYOUT
0100- 207-10- G BUILDING- METER PANEL ROOM LAYOUT
0100- 207-11- G BUILDING- ELECTRICAL & LV DUCT LOCATION LAYOUT
0100- 207-12- G BUILDING- FIRE ALARM SYSTEM LAYOUT
0100- 207-13- G BUILDING- CCTV SYSTEM LAYOUT
0100- 207-14- G BUILDING- FLAT INTERNAL SLD FOR 1RK FLATS
0100- 207-15- G BUILDING- FLAT INTERNAL SLD FOR 1 BHK FLATS
0100- 207-16- G BUILDING- FLAT INTERNAL SLD FOR 2 BHK FLATS
0100- 207-17- G BUILDING- FLAT INTERNAL SLD FOR 3 BHK FLATS
0100- 207-18- G BUILDING- METER PANEL SLD
0100- 207-19- G BUILDING-CABLE TRAY LAYOUT FROM METER PANEL TO DUCT
0100- 207-20- G BUILDING-COMMON METER DB SLD
0100- 207-21- G BUILDING-TERRACE FLOOR LIGHTING & POWER LAYOUT

## DR
E - BUILDING | 0100-101- LOWER GROUND CONTROL & CONDUIT LAYOUT | 0100-201- ELECTRICAL BOQ & ESTIMATE
| 0100-102- UPPER GROUND CONTROL & CONDUIT LAYOUT | 0100-202- FIRE ALARM SYSTEM BOQ & ESTIMATE
| 0100-103- GROUND FLOOR CONTROL & CONDUIT LAYOUT | 0100-203- CCTV SYSTEM BOQ & ESTIMATE
| 0100-104- FIRST FLOOR CONTROL & CONDUIT LAYOUT | 0100-204- TYPICAL 1RK FLATS SWITCH BOARD DETAILS
| 0100-105- TYPICAL EVEN FLOOR CONTROL & CONDUIT LAYOUT | 0100-205- TYPICAL 1 BHK FLATS SWITCH BOARD DETAILS
| 0100-106- TYPICAL ODD FLOOR CONTROL LAYOUT | 0100-206- TYPICAL 2 BHK FLATS SWITCH BOARD DETAILS
| 0100-107- SAMPLE FLAT CONTROL & CONDUIT LAYOUT | 0100-207- TYPICAL 3 BHK FLATS SWITCH BOARD DETAILS
0100-108- REFUSE FLOOR-1 CONTROL & CONDUIT LAYOUT
0100-109- REFUSE FLOOR-2 CONTROL & CONDUIT LAYOUT
0100-110- METER PANEL ROOM LAYOUT
0100-111- ELECTRICAL & LV DUCT LOCATION LAYOUT
0100-112- FIRE ALARM SYSTEM LAYOUT
0100-113- CCTV SYSTEM LAYOUT
0100-114- FLAT INTERNAL SLD FOR 1RK FLATS
0100-115- FLAT INTERNAL SLD FOR 1 BHK FLATS
0100-116- FLAT INTERNAL SLD FOR 2 BHK FLATS
0100-117- FLAT INTERNAL SLD FOR 3 BHK FLATS
0100-118- METER PANEL SLD
0100-119- CABLE TRAY LAYOUT FROM METER PANEL TO DUCT
0100-120- COMMON METER DB SLD
0100-121- TERRACE FLOOR LIGHTING & POWER LAYOUT
HOSPITAL PROJECT
INDUSTRIAL PROJECT
COMMERCIAL PROJECT

## Sheet1
0200-101- Basement Floor Drainage Layout
0200-102- Terrace Looping Layout
0200-103- Water Supply System Diagram Layout
0200-104- Ceiling Diversion Layout
0200-105- Plumbing Layout Plan
0200-106- OHT Details Layout